## Overview
AKFA Trading Group
NCA ECC ↔ ISO/IEC 27001:2022 Mapping Matrix
NCA Essential Cybersecurity Controls (ECC-2:2024) ¦ Version 1.0 ¦ January 2026 ¦ Prepared by: Reem Ibrahim
Purpose | Maps the 28 subdomains of the Saudi NCA Essential Cybersecurity Controls (ECC-2:2024, 4 domains / 108 controls) to ISO/IEC 27001:2022 Annex A controls and to the organization's risk register, showing alignment status and planned treatment actions.
Why both | ISO 27001 provides the ISMS framework; NCA ECC is the national regulatory baseline for in-scope Saudi entities. One control set implemented well can satisfy both — this matrix shows where they meet.
Status key | Aligned = requirement substantially met · Partially aligned = control exists but immature · Gap = not yet implemented (treatment action referenced where planned).
Inputs | Risk register (AKFA_Risk_Register.xlsx), Statement of Applicability, treatment plan T-01 to T-12.
Alignment Summary
Aligned | 1
Partially aligned | 17
Gap | 10
Total subdomains | 28

## Mapping
ECC Ref | ECC Subdomain (EN) | النطاق الفرعي (AR) | ECC Domain | ISO 27001:2022 Mapping | Related Risks | Alignment | Notes / Treatment Reference
1-1 | Cybersecurity Strategy | استراتيجية الأمن السيبراني | Governance | A.5.1; Clause 5.1, 5.2 |  | Partially aligned | Security strategy to be formalized and approved by executive management.
1-2 | Cybersecurity Management | إدارة الأمن السيبراني | Governance | A.5.2, A.5.4 |  | Partially aligned | ISO function assigned; steering committee to be established.
1-3 | Cybersecurity Policies and Procedures | سياسات وإجراءات الأمن السيبراني | Governance | A.5.1, A.5.37 |  | Partially aligned | Policy suite in development; operating procedures partially documented.
1-4 | Cybersecurity Roles and Responsibilities | أدوار ومسؤوليات الأمن السيبراني | Governance | A.5.2, A.5.3 | R-03, R-08 | Partially aligned | RACI needed across the 7 divisions; segregation of duties in finance.
1-5 | Cybersecurity Risk Management | إدارة مخاطر الأمن السيبراني | Governance | Clause 6.1.2, 8.2; A.5.8 | All | Aligned | This assessment establishes the risk management process and register.
1-6 | Cybersecurity in IT Project Management | الأمن السيبراني ضمن إدارة المشاريع التقنية | Governance | A.5.8 |  | Gap | Security requirements not yet embedded in project lifecycle.
1-7 | Compliance with Cybersecurity Standards, Laws and Regulations | الالتزام بتشريعات وتنظيمات الأمن السيبراني | Governance | A.5.31, A.5.36 | R-12 | Partially aligned | PDPL compliance review planned Q2 2026.
1-8 | Periodical Cybersecurity Review and Audit | المراجعة والتدقيق الدوري للأمن السيبراني | Governance | A.5.35, A.8.34 |  | Gap | No independent security review performed to date.
1-9 | Cybersecurity in Human Resources | الأمن السيبراني المتعلق بالموارد البشرية | Governance | A.6.1, A.6.2, A.6.5 | R-08 | Partially aligned | Screening and NDAs in place; leaver deprovisioning SLA missing.
1-10 | Cybersecurity Awareness and Training Program | برنامج التوعية والتدريب بالأمن السيبراني | Governance | A.6.3 | R-01, R-18 | Gap | Program launch planned Q1 2026 (treatment T-03).
2-1 | Asset Management | إدارة الأصول | Defense | A.5.9, A.5.10, A.5.11 |  | Partially aligned | Asset register created in this assessment; lifecycle process to mature.
2-2 | Identity and Access Management | إدارة هويات الدخول والصلاحيات | Defense | A.5.15–A.5.18, A.8.2, A.8.5 | R-01, R-04, R-05 | Gap | Highest-priority gap: tenant-wide MFA (T-01) and PAM (T-02).
2-3 | Information System and Processing Facilities Protection | حماية الأنظمة وأجهزة معالجة المعلومات | Defense | A.8.7, A.8.9, A.8.19 | R-13 | Partially aligned | EDR and allow-listing planned Q2 2026 (T-06).
2-4 | Email Protection | حماية البريد الإلكتروني | Defense | A.5.14, A.8.7 | R-01, R-03 | Partially aligned | Spam filtering active; DMARC/DKIM/SPF enforcement pending (T-01/T-03).
2-5 | Networks Security Management | إدارة أمن الشبكات | Defense | A.8.20, A.8.21, A.8.22 | R-02, R-11 | Partially aligned | Segmentation of production/backup networks planned (T-06).
2-6 | Mobile Devices Security | أمن الأجهزة المحمولة | Defense | A.8.1, A.6.7, A.7.9 | R-14 | Partially aligned | Intune enrollment underway; disk encryption enforcement Q1 2026 (T-10).
2-7 | Data and Information Protection | حماية البيانات والمعلومات | Defense | A.5.12, A.5.13, A.5.33, A.8.10–A.8.12 | R-09, R-12 | Gap | Classification and DLP program planned Q3 2026 (T-08).
2-8 | Cryptography | التشفير | Defense | A.8.24 | R-12, R-14 | Partially aligned | TLS in transit; encryption at rest for HR/finance data to be extended.
2-9 | Backup and Recovery Management | إدارة النسخ الاحتياطية | Defense | A.8.13 | R-02, R-07 | Partially aligned | Daily backups run; restore testing and offline copy planned Q1 2026 (T-05).
2-10 | Vulnerabilities Management | إدارة الثغرات | Defense | A.8.8 | R-06 | Gap | No formal patch cycle; monthly cadence planned Q2 2026 (T-04).
2-11 | Penetration Testing | اختبار الاختراق | Defense | A.5.35, A.8.8, A.8.34 | R-06 | Gap | No penetration testing performed; recommend annual scope post-remediation.
2-12 | Cybersecurity Event Logs and Monitoring Management | إدارة سجلات الأحداث والمراقبة | Defense | A.8.15, A.8.16, A.8.17 | R-04 | Partially aligned | System logs exist; centralized monitoring/alerting planned.
2-13 | Cybersecurity Incident and Threat Management | إدارة حوادث وتهديدات الأمن السيبراني | Defense | A.5.7, A.5.24–A.5.28, A.6.8 | R-01, R-02 | Gap | IR plan and playbooks planned; NCA incident reporting channel to be defined.
2-14 | Physical Security | الأمن المادي | Defense | A.7.1–A.7.4, A.7.14 | R-16 | Partially aligned | Badge access and CCTV for server room planned Q3 2026 (T-12).
2-15 | Web Application Security | حماية تطبيقات الويب | Defense | A.8.20, A.8.23, A.8.26* | R-17 | Partially aligned | Limited public web footprint; *A.8.26 excluded in SoA (no in-house development) — vendor-supplied apps governed via supplier controls.
3-1 | Cybersecurity Resilience Aspects of BCM | جوانب الصمود السيبراني في استمرارية الأعمال | Resilience | A.5.29, A.5.30, A.8.14 | R-07, R-11 | Gap | DR runbook and WAN redundancy planned Q3 2026 (T-11).
4-1 | Third-Party Cybersecurity | الأمن السيبراني المتعلق بالأطراف الخارجية | Third-Party & Cloud | A.5.19–A.5.22 | R-10 | Gap | Vendor security assessment program planned Q3 2026 (T-07).
4-2 | Cloud Computing and Hosting Cybersecurity | الأمن السيبراني للحوسبة السحابية والاستضافة | Third-Party & Cloud | A.5.23 | R-15 | Partially aligned | M365 governed; SaaS discovery and approval process planned Q4 2026.